## Metrics Table
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
CPI | 1.0806 | 1.164 | 1.0385 | 1.25 | 0.5875 | 0.65 | 0.95192 | 0.97
RCM | 0 | 0.26667 | 0.4 | 0.46667 | 0.53333 | 0.63333 | 0.8 | 1
Error Density | 0 | 0.33333 | 0.6 | 0.4 | 0.5 | 0.41667 | 0.3 | 0
MTTF | 0 | 19.2 | 18.6667 | 22 | 40 | 24 | 37.3333 | 96
MTTR | 0 | 3 | 2.4 | 3.1667 | 2.6667 | 1.7 | 1.9167 | 1
AVAIL. | 0 | 86.4865 | 88.6076 | 87.4172 | 93.75 | 93.3852 | 95.1168 | 98.9691
SMI | 0 | 0.14286 | 0.15385 | 0.4375 | 0.55 | 0.64 | 0.70968 | 1

## Calculations
Week | Requirement Length (1 = 1week) | Budgeted Proportion of Time For Lead On Req (1 = 1 week) | Lead Hours/Month | BCWP | ACWP | CPI | RCM | Error Density | MTTR | MTTF | AVAIL | SMI | Error Density Calculation | Error Total | WPS = # of requirements for that cycle | MTTR Calculations | total maintenance time to fix (hours) | total # of repairs | MTTF Calculations | total # of hours spent to find it | total hours of operation (span of days passed) | SMI Calculations | Mt = # of modules in the current release | Fa = Mt added | Fc = Mt changed | Fd = Mt deleted | Total reqs completed
1 | 1 | 1 | 32 | 33.5 | 31 | 1.0806 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4 |  | 0 | 0 |  | 0 | 0 |  | 4 | 4 | 0 | 0 | 0
2 | 1 | 0.925 | 32 | 29.1 | 25 | 1.164 | 0.24242 | 0.33333 | 3 | 0 | 0 | 0.14286 |  | 2 | 6 |  | 6 | 2 |  | 1 | 0 |  | 7 | 4 | 3 | 1 | 8
3 | 1 | 0.825 | 32 | 27 | 26 | 1.0385 | 0.36364 | 0.6 | 2.4 | 0 | 0 | 0.15385 |  | 6 | 10 |  | 12 | 5 |  | 4.5 | 0 |  | 13 | 7 | 3 | 1 | 12
4 | 1 | 0.925 | 32 | 29.25 | 26 | 1.125 | 0.46667 | 0.4 | 3.1667 | 0 | 0 | 0.4375 |  | 4 | 10 |  | 9.5 | 3 |  | 3 | 0 |  | 16 | 4 | 4 | 1 | 14
5 | 0.75 | 0.75 | 32 | 23.5 | 20 | 1.175 | 0.53333 | 0.5 | 2.6667 | 0 | 0 | 0.55 |  | 5 | 10 |  | 8 | 3 |  | 3 | 0 |  | 20 | 5 | 3 | 1 | 16
6 | 0.75 | 0.625 | 32 | 19.5 | 21 | 0.92857 | 0.63333 | 0.41667 | 1.7 | 0 | 0 | 0.64 |  | 5 | 12 |  | 8.5 | 5 |  | 2.5 | 0 |  | 25 | 6 | 2 | 1 | 19
7 | 1 | 0.8 | 32 | 24.75 | 26 | 0.95192 | 0.8 | 0.3 | 1.9167 | 0 | 0 | 0.70968 |  | 3 | 10 |  | 11.5 | 6 |  | 4.5 | 0 |  | 31 | 6 | 3 | 0 | 24
8 | 1 | 0.925 | 32 | 29.1 | 30 | 0.97 | 1 | 0 | 1 | 0 | 0 | 1 |  | 0 | 10 |  | 4 | 4 |  | 3 | 0 |  | 31 | 0 | 0 | 0 | 30
Indvidual Reports
1 | 1 | 1 | 40 | 10 | 8 | 1.25 | Larry | [6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 0 | Larry
2 | 1 | 1 | 32 | 8 | 7 | 1.1429 | [7 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 |  |  | 1 | 1 | 0
3 | 1 | 1 | 35 | 8.75 | 8 | 1.0938 | [7 empty] | 2 |  |  | 2 | 2 |  | 1 | 0.25 |  |  | 2 | 1 | 1
4 | 1 | 1 | 32 | 8 | 7 | 1.1429 | [7 empty] | 2 |  |  | 0 | 0 |  | 1 | 0.25 |  |  | 2 | 1 | 1
5 | 1 | 1 | 32 | 8 | 8 | 1 | [7 empty] | 2 |  |  | 1 | 1 |  | 1 | 2 |  |  | 2 | 1 | 0
6 | 1 | 0.5 | 32 | 4 | 8 | 0.5 | [7 empty] | 2 |  |  | 2 | 2 |  | 1 | 1 |  |  | 2 | 2 | 1
7 | 1 | 0.7 | 30 | 5.25 | 4 | 1.3125 | [7 empty] | 2 |  |  | 2 | 2 |  | 1 | 2 |  |  | 2 | 1 | 0
8 | 1 | 0.7 | 32 | 5.6 | 4 | 1.4 | [7 empty] | 0 |  |  | 1 | 1 |  | 0 | 3 |  |  | 0 | 0 | 0
0
1 | 1 | 1 | 32 | 8 | 8 | 1 | Luke | [6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 0 | Luke
2 | 1 | 0.7 | 32 | 5.6 | 5 | 1.12 | [7 empty] | 1 |  |  | 3 | 1 |  | 0.5 | 0.5 |  |  | 1 | 1 | 1
3 | 1 | 1 | 32 | 8 | 7 | 1.1429 | [7 empty] | 2 |  |  | 2 | 1 |  | 1 | 0.25 |  |  | 2 | 0 | 0
4 | 1 | 1 | 32 | 8 | 8 | 0 | [7 empty] | 1 |  |  | 3 | 1 |  | 1 | 1 |  |  | 2 | 1 | 0
5 | 0 | 0 | 32 | 0 | 0 | 0 | [7 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0
6 | 0 | 0 | 32 | 0 | 0 | 0 | [7 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0
7 | 1 | 0.5 | 32 | 4 | 6 | 0.66667 | [7 empty] | 1 |  |  | 3 | 1 |  | 2 | 2 |  |  | 2 | 1 | 0
8 | 1 | 1 | 32 | 8 | 10 | 0.8 | [7 empty] | 0 |  |  | 1 | 1 |  | 1.5 | 3 |  |  | 0 | 0 | 0
1 | 1 | 1 | 30 | 7.5 | 8 | 0.9375 | Nima | [6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 0 | Nima
2 | 1 | 1 | 30 | 7.5 | 6 | 1.25 | [7 empty] | 1 |  |  | 0 | 0 |  | 0 | 0 |  |  | 1 | 1 | 0
3 | 1 | 0.3 | 30 | 2.25 | 3 | 0.75 | [7 empty] | 1 |  |  | 4 | 1 |  | 2 | 1 |  |  | 2 | 1 | 0
4 | 1 | 0.7 | 30 | 5.25 | 5 | 1.05 | [7 empty] | 0 |  |  | 3.5 | 1 |  | 0.5 | 0.5 |  |  | 0 | 1 | 0
5 | 1 | 1 | 30 | 7.5 | 5 | 1.5 | [7 empty] | 0 |  |  | 3.5 | 1 |  | 1 | 1 |  |  | 1 | 1 | 0
6 | 1 | 1 | 30 | 7.5 | 6 | 1.25 | [7 empty] | 2 |  |  | 3 | 1 |  | 0.5 | 0.5 |  |  | 2 | 0 | 0
7 | 1 | 1 | 30 | 7.5 | 7 | 1.0714 | [7 empty] | 0 |  |  | 3.5 | 1 |  | 1 | 1 |  |  | 1 | 0 | 0
8 | 1 | 1 | 30 | 7.5 | 7 | 1.0714 | [7 empty] | 0 |  |  | 1 | 1 |  | 0.5 | 3 |  |  | 0 | 0 | 0
1 | 1 | 1 | 32 | 8 | 7 | 1.1429 | Annie | [6 empty] | 0 |  |  | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 0 | Annie
2 | 1 | 1 | 32 | 8 | 7 | 1.1429 | [7 empty] | 0 |  |  | 3 | 1 |  | 0.5 | 0.3 |  |  | 1 | 0 | 0
3 | 1 | 1 | 32 | 8 | 8 | 1 | [7 empty] | 1 |  |  | 4 | 1 |  | 0.5 | 2 |  |  | 1 | 1 | 0
4 | 1 | 1 | 32 | 8 | 6 | 1.3333 | [7 empty] | 1 |  |  | 3 | 1 |  | 0.5 | 1 |  |  | 0 | 1 | 0
5 | 1 | 1 | 32 | 8 | 7 | 1.1429 | [7 empty] | 3 |  |  | 3.5 | 1 |  | 1 | 2 |  |  | 2 | 1 | 1
6 | 1 | 1 | 32 | 8 | 7 | 1.1429 | [7 empty] | 1 |  |  | 3.5 | 2 |  | 1 | 1 |  |  | 2 | 0 | 0
7 | 1 | 1 | 32 | 8 | 9 | 0.88889 | [7 empty] | 0 |  |  | 3 | 2 |  | 0.5 | 2 |  |  | 1 | 1 | 0
8 | 1 | 1 | 32 | 8 | 9 | 0.88889 | [7 empty] | 0 |  |  | 1 | 1 |  | 1 | 3 |  |  | 0 | 0 | 0