## 02272022 (hidden)
# | Software Requirement | Acceptance Criteria | Module | FP Score | Effort Score | Priority | Phase | Bold = Main tasks
1 | Given a customer, the customer should be able to see a menu. | Given a customer, the customer should be able to view all products' name, price, and description sold by Maui Chicken. | Frontend | 138.56 | 375.846 | H | 1.1 | Other = subtasks
2 | Given a customer, the customer should be able to select a quantity and purchase a product(s) by clicking on the appropriate field below the description to add to shopping cart. | Given I am a customer, when I increase the quantity for a product I am ordering, then the quantity I have selected will be the quantity accounted for in my order. | Frontend | 138.5 | 3002.864 | H | 1.2
3 | Given a customer, the customer should be able to identify food based on their preferences. | Given I am a customer, when I see a menu item tagged with a symbol, then I will know that the specific item has a characteristic that could abide to a dietary or flavor preference | Frontend | 95.9 | 36.9214 | L | 1.3 | Lead
4 | Given a customer, the customer will see the restaurant's recommendation in a page. | Given I am a customer, when I open the restaurant's menu page, then I will see a list of recommendations made by the restaurant | Frontend | 53.29 | 1.3705 | L | 2.1 | Larry Delgado
5 | Given a customer, the customer should be able to contact any given Maui Chicken restaurant location. | Given I am a customer who needs assistance, when I select a phone number for a specified location, then I will be able to call the restaurant and speak to a Maui Chicken worker. | Frontend | 159.87 | 21.3813 | M | 1.4 | Annie Tran
6 | Given an owner, the owner's restaurant will generate a global QR code amongst all locations for the customer. | Given I am the owner, when I generate a global QR code for my website, then whenever anyone scans that QR code they will be taken to the restaurant's website | Backend | 159.87 | 4618.3541 | H | 2.5 | Luke Sunoaka
7 | Given a customer, the customer will use their device's camera to scan the QR code. | Given I am a customer, when I scan the QR code with my camera, then I will be redirected to the restaurant's website | Frontend | 63.97 | 4618.3541 | H | 2.6 | Nima Fathali Siah
8 | Given an employee, the employee should be able to manually set a timer on when the customer’s order will be ready. | Given a customer, the customer should be able to view how long their order will take. | Backend | 213.13 | 36.985 | L | 3.1
9 | Given a customer, the customer should be able to make an order. | Given I am a customer who has already placed an order, when I select to review my order, then I will be directed to a page that contains information regarding my previous order. | Frontend | 181.15 | 10942.5882 | H | 3.2
10 | Given a customer, the customer should be able to review their orders made earlier. | Given I am a customer who has already placed an order, when I select to review my order, then I will be directed to a page that contains information regarding my previous order | Frontend | 117.21 | 6718.9486 | H | 3.3
11 | As a customer, I should be able to pick a location upon placing my order. | Given I am a customer, once I finish an order and select a location, then my order will be sent to that location | Frontend | 106.56 | 67.4088 | M | 3.4
12 | Given a customer, the customer should be able to know how to cancel their order. | Given I am a customer who wants to cancel an order, when I look on the webpage, then I should be able to view a cancel button and be notified of the process | Frontend | 85.3 | 50.653 | H | 4.1
13 | Given a customer, the customer should be able to add a order to the order queue. | Given I am a customer, when I place an order, that order will automatically be added to the order queue | Backend | 85.3 | 87.6887 | H | 3.5
14 | Given an employee, the employee should be able to view the order queue. | Given I am an aployee, when I attempt to view the order queue, then I will be able to see the internal queue for orders and their information | Backend | 85.29 | 87.6578 | H | 4.4
15 | Given an owner, the owner should be able to access back-end only website where all order transactions are made. | Given I am an owner, when I log in to the website, then I will be able to access and view information and transactions unviewable otherwise | Backend | 53.37 | 171.8217 | H | 4.2
16 | Given an employee, the employee should be able to access back-end only website where all order transactions are made. | Given I am an employee, when I log in to the website, then I will be able to access and view information and transactions unviewable otherwise | Backend | 53.37 | 171.8217 | H | 4.3
17 | As an employee, the employee can notify a customer by phone recorded on a log if the order isn't picked up within a set time. | Given I am an employee, when an order is not picked up on time, then I can notify the customer by checking the number tied to that order | Backend | 42.67 | 3.2523 | L | 4.5
18 | As an employee, the employee wants to know which delivery order is being picked up by whom. | Given I am an employee, when a customer places an order for pick up, I will know who will be picking it up | Backend | 63.97 | 36.985 | L | 4.6
19 | As an employee, the employee should be able to manage the menu inventory on whether the menu is still available. | Given I am an employee, when I change inventory for menu items, it should reflect on the website as available or not available | Backend | 42.71 | 88.0593 | M | 4.7
20 | As a customer, the customer should know if a menu item is available upon ordering. If isn't, they will alerted by the location, and it will be removed from their shopping cart. | Given I am a customer, when I order something that isn't available, it will not be ordered and I will receive a notification that it is unavailable | Middleware | 42.7 | 87.9974 | M | 4.8
21 | As an employee, the order should reach my location to enter the queue. | Given I am an employee, when I receive an order, then it should enter queue | Backend | 74.61 | 58.6796 | M | 3.6
22 | As an owner, the owner wants an updated and clean displayment of restaurant information. | Given I am the owner, when I update information regarding the restaurant, then it will reflect on the website itself | Backend | 42.66 | 87.75 | H | 1.5
23 | As a owner, the owner should be able to update any product information as well as any menu change. | Given I am the owner, when I update information regarding the menu, then it will reflect on the website's menu | Backend | 85.26 | 700.523 | H | 2.4
24 | As a owner, the customer should be able to view any changes made to the website | Given I am the owner, when I update the website in any way, then the customer should be able to view it | Frontend | 127.87 | 2363.155 | H | 1.6
25 | As an owner, the owner wants to take in online orders without being liable for any security leaks. | The Square API will handle the transaction liabilities. | Backend | 0.04 | 0.007 | L | 3.7
26 | As an owner, the owner wants to promote their Yelp restaurant page on the website. | A Yelp Image Icon button will appear on the homepage that is a link to the restauraunt yelp page. | Frontend | 0.04 | 0.007 | L | 1.7
27 | As an employee, the employee can notify a customer by phone recorded on a log if the order isn't picked up within a set time. | A customer will be called according to the phone number they provided in their order details found in the queue or database logs | Backend | 53.29 | 21.38 | L | 4.9
28 | As a customer, the customer should be given the ability to pay online by credit card form. | After pressing a checkout button the screen loads payment form from the Square 3rd party API | Backend | 21.37 | 11.03 | H | 3.8
29 | As a customer, the customer should be able to view the payment screen with all of their orders listed and submit their order. | A sub-total count with order details will appear before entering checkout. | Frontend | 32.02 | 4.62 | M | 2.2
30 | As a customer, the customer should be able to view their shopping cart. | A shopping cart page should load that contains any pending orders before a checkout button, with the option to change quantity | Frontend | 53.32 | 21.41 | H | 2.3
31 | As a customer, the customer should be able to receive a downloadable receipt. | Upon receiving a receipt, it should be a downloadable file to my device. | Frontend | 32.02 | 1.37 | H | 3.9
32 | As a owner, the owner should be able to send a receipt about a order that has just been placed to the respective customer. | A receipt should be able to be created on a page through the web application | Backend | 31.97 | 1.36 | H | 3.1.5
33 | As a owner, I would like to log all orders made by customers in the past and log them for three days. Logs past three days will be deleted. | Logs should be visible for at least 3 days in the databaes, any longer the logs will be deleted. | Backend | 32.02 | 4.638 | M | 4.9.5

## 03062022 (hidden)
# | Software Requirement | Acceptance Criteria | Module | FP Score | Effort Score | Priority |  | Bold = Main tasks
1 | Given a customer, the customer should be able to make an order. | Given I am a customer who has already placed an order, when I select to review my order, then I will be directed to a page that contains information regarding my previous order. | Frontend | 181.15 | 875.2978 | H | 3.2 | Other = subtasks
2 | Given a customer, the customer should be able to review their orders placed earlier. | Given I am a customer who has already placed an order, when I select to review my order, then I will be directed to a page that contains information regarding my previous order | Frontend | 117.21 | 874.8631 | H | 3.3
3 | Given a customer, the customer will use their device's camera to scan the QR code and obtain the menu | Given I am a customer, when I scan the QR code with my camera, then I will be redirected to the restaurant's website | Frontend | 63.97 | 601.3482 | H | 2.6 | Lead
4 | Given a customer, the customer should be able to know how to cancel their order in a simple manner. | Given I am a customer who wants to cancel an order, when I look on the webpage, then I should be able to view a cancel button and be notified of the process | Frontend | 85.3 | 488.4074 | H | 4.1 | Larry Delgado
5 | Given an owner, the owner's restaurant will generate a global QR code amongst all locations for the customer. | Given I am the owner, when I generate a global QR code for my website, then whenever anyone scans that QR code they will be taken to the restaurant's website | Backend | 159.87 | 391.591 | H | 2.5 | Annie Tran
6 | Given a customer, the customer should be able to see a menu from any web accessible application | Given a customer, the customer should be able to view all products' name, price, and description sold by Maui Chicken. | Frontend | 138.56 | 391.5063 | H | 1.1 | Luke Sunoaka
7 | Given a customer, the customer should be able to select a quantity and purchase a product(s) by clicking on the appropriate field below the description to add to shopping cart. | Given I am a customer, when I increase the quantity for a product I am ordering, then the quantity I have selected will be the quantity accounted for in my order. | Frontend | 138.5 | 390.9979 | H | 1.2 | Nima Fathali Siah
8 | As a owner, the customer should be able to view any changes made to the website so that any special promotions willl not go unnoticed. | Given I am the owner, when I update the website in any way, then the customer should be able to view the changes I have applied. | Frontend | 127.87 | 307.7025 | H | 1.6
9 | Given an owner, the owner should be able to access back-end only website where all order transactions are made. | Given I am an owner, when I log in to the website, then I will be able to access and view information and transactions unviewable otherwise | Backend | 53.37 | 178.9809 | H | 4.2
10 | Given an employee, the employee should be able to access back-end only website where all order transactions are made. | Given I am an employee, when I log in to the website, then I will be able to access and view information and transactions unviewable otherwise | Backend | 53.37 | 178.9809 | H | 4.3
11 | As an owner, the owner wants to take in online orders without being liable for any security leaks. | Given I am the ower, I would like all liabilities regarding online payment to be unrelated to me. This could be obtained by using a third party API such as Square. | Backend | 0.04 | 178.2776 | L | 3.7
12 | As an owner, the owner wants to promote their Yelp restaurant page on the website. | Given I am the owner, I woud like for my Yelp page to be promoted so that my customer's can see any other customer reviews made. | Frontend | 0.04 | 178.2776 | L | 1.7
13 | As an employee, the employee should be able to manage the menu inventory on whether the menu is still available. | Given I am an employee, when I change inventory for menu items, it should reflect on the website as available or not available | Backend | 42.71 | 91.7284 | M | 4.7
14 | As a customer, the customer should know if a menu item is available upon ordering. If isn't, they will alerted by the location, and it will be removed from their shopping cart. | Given I am a customer, when I order something that isn't available, it will not be ordered and I will receive a notification that it is unavailable | Middleware | 42.7 | 91.664 | M | 4.8
15 | As an owner, the owner wants an updated and clean displayment of restaurant information. | Given I am the owner, when I update information regarding the restuarant, then it will reflect on the website itself | Backend | 42.66 | 91.4066 | H | 1.5
16 | Given a customer, the customer should be able to add a order to the order queue of customer orders. | Given I am a customer, when I place an order, that order will automatically be added to the order queue | Backend | 85.3 | 91.3423 | H | 3.5
17 | Given an employee, the employee should be able to view the order queue of all orders made within the restaurant. | Given I am an aployee, when I attempt to view the order queue, then I will be able to see the internal queue for orders and their information | Backend | 85.29 | 91.3102 | H | 4.4
18 | As a owner, the owner should be able to update any product information as well as any menu change. | Given I am the owner, when I update information regarding the menu, then it will reflect on the website's menu | Backend | 85.26 | 91.2139 | H | 2.4
19 | As a customer, I should be able to pick a location upon placing my order out of all three locations. | Given I am a customer, once I finish an order and select a location, then my order will be sent to that location | Frontend | 106.56 | 70.2175 | M | 3.4
20 | As an employee, the order should reach my location to enter the queue of other orders made within the restaurant. | Given I am an employee, when I receive an order, then it should enter queue | Backend | 74.61 | 61.1246 | M | 3.6
21 | Given an employee, the employee should be able to manually set a timer on when the customer’s order will be ready. | Given a customer, the customer should be able to view how long their order will take. | Backend | 213.13 | 38.526 | L | 3.1
22 | As an employee, the employee wants to know which delivery order is being picked up by whom in order to keep customer orders organized. | Given I am an employee, when a customer places an order for pick up, I will know who will be picking it up | Backend | 63.97 | 38.526 | L | 4.6
23 | As a customer, the customer should be able to view the payment screen with all of their orders listed and submit their order. | Given I am a customer, I would like to see a sub-total count with order details will appear before entering checkout. | Frontend | 32.02 | 38.508 | M | 2.2
24 | Given a customer, the customer should be able to identify food based on their preferences in a simple, organized display made on the menu. | Given I am a customer, when I see a menu item tagged with a symbol, then I will know that the specific item has a characteristic that could abide to a dietary or flavor preference | Frontend | 95.9 | 38.4598 | L | 1.3
25 | As a customer, the customer should be able to view their shopping cart. and check what they have ordered so far. | A shopping cart page should load that contains any pending orders before a checkout button, with the option to change quantity | Frontend | 53.32 | 22.3098 | H | 2.3
26 | Given a customer, the customer should be able to contact any given Maui Chicken restaurant location. | Given I am a customer who needs assistance, when I select a phone number for a specified location, then I will be able to call the restaurant and speak to a Maui Chicken worker. | Frontend | 159.87 | 22.2722 | M | 1.4
27 | As an employee, the employee can notify a customer by phone recorded on a log if the order isn't picked up within a set time. | A customer will be called according to the phone number they provided in their order details found in the queue or database logs | Backend | 53.29 | 22.2722 | L | 4.5
28 | As a customer, the customer should be given the ability to pay online by credit card form. | Given I am a customer, I should be able to pay for my order online through a simple click of a button. Furthermore, the payment system should be easy and self intuitive. | Backend | 21.37 | 11.4902 | H | 3.8
29 | As an employee, the employee can notify a customer by phone recorded on a log if the order isn't picked up within a set time. | Given I am an employee, when an order is not picked up on time, then I can notify the customer by checking the number tied to that order | Backend | 42.67 | 11.4339 | L | 4.9
30 | As a owner, I would like to log all orders made by customers in the past and log them for three days. Logs past three days will be deleted. | As a owner, I should be able to review all recorded logs in my database for at least 3 days. After 3 days, these logs will get deleted unless specified. | Backend | 32.02 | 4.8316 | M | 4.9.5
31 | As a owner, the owner should be able to send a receipt about a order that has just been placed to the respective customer. | As a owner, I should be able to provide customer with a receipt regarding the order that they just placed on top of being able to review the customer's order. | Backend | 31.97 | 4.809 | H | 3.1.5
32 | As a customer, the customer should be able to receive a downloadable receipt. | As a customer, when I place my online order, I would like a digital copy of my receipt to review my order. | Frontend | 32.02 | 1.4316 | H | 3.9
33 | Given a customer, the customer will see the restaurant's recommendation at the home page. | As a customer, I would like to see what Maui Chicken has to offer and would like details about the restuarant's recomendations | Frontend | 53.29 | 1.4276 | L | 2.1

## 03202022
2022-03-20
# | Software Requirement | Acceptance Criteria | Module | FP Score | Effort Score | Priority |  | Bold = Main tasks
1 | Given a customer, the customer should be able to make an order. | Given I am a customer who has already placed an order, when I select to review my order, then I will be directed to a page that contains information regarding my previous order. | Frontend | 181.15 | 875.2978 | H | 3.2 | Other = subtasks
2 | Given a customer, the customer should be able to review their orders placed earlier. | Given I am a customer who has already placed an order, when I select to review my order, then I will be directed to a page that contains information regarding my previous order | Frontend | 117.21 | 874.8631 | H | 3.3
3 | Given a customer, the customer will use their device's camera to scan the QR code and obtain the menu | Given I am a customer, when I scan the QR code with my camera, then I will be redirected to the restaurant's website | Frontend | 63.97 | 601.3482 | H | 2.6 | Lead
4 | Given a customer, the customer should be able to know how to cancel their order in a simple manner. | Given I am a customer who wants to cancel an order, when I look on the webpage, then I should be able to view a cancel button and be notified of the process | Frontend | 85.3 | 488.4074 | H | 4.1 | Larry Delgado
5 | Given an owner, the owner's restaurant will generate a global QR code amongst all locations for the customer. | Given I am the owner, when I generate a global QR code for my website, then whenever anyone scans that QR code they will be taken to the restaurant's website | Backend | 159.87 | 391.591 | H | 2.5 | Annie Tran
6 | Given a customer, the customer should be able to see a menu from any web accessible application | Given a customer, the customer should be able to view all products' name, price, and description sold by Maui Chicken. | Frontend | 138.56 | 391.5063 | H | 1.1 | Luke Sunoaka
7 | Given a customer, the customer should be able to select a quantity and purchase a product(s) by clicking on the appropriate field below the description to add to shopping cart. | Given I am a customer, when I increase the quantity for a product I am ordering, then the quantity I have selected will be the quantity accounted for in my order. | Frontend | 138.5 | 390.9979 | H | 1.2 | Nima Fathali Siah
8 | As a owner, the customer should be able to view any changes made to the website so that any special promotions willl not go unnoticed. | Given I am the owner, when I update the website in any way, then the customer should be able to view the changes I have applied. | Frontend | 127.87 | 307.7025 | H | 1.6
9 | Given an owner, the owner should be able to access back-end only website where all order transactions are made. | Given I am an owner, when I log in to the website, then I will be able to access and view information and transactions unviewable otherwise | Backend | 53.37 | 178.9809 | H | 4.2
10 | Given an employee, the employee should be able to access back-end only website where all order transactions are made. | Given I am an employee, when I log in to the website, then I will be able to access and view information and transactions unviewable otherwise | Backend | 53.37 | 178.9809 | H | 4.3
11 | As an owner, the owner wants to take in online orders without being liable for any security leaks. | Given I am the ower, I would like all liabilities regarding online payment to be unrelated to me. This could be obtained by using a third party API such as Square. | Backend | 0.04 | 178.2776 | L | 3.7
12 | As an owner, the owner wants to promote their Yelp restaurant page on the website. | Given I am the owner, I woud like for my Yelp page to be promoted so that my customer's can see any other customer reviews made. | Frontend | 0.04 | 178.2776 | L | 1.7
13 | As an employee, the employee should be able to manage the menu inventory on whether the menu is still available. | Given I am an employee, when I change inventory for menu items, it should reflect on the website as available or not available | Backend | 42.71 | 91.7284 | M | 4.7
14 | As a customer, the customer should know if a menu item is available upon ordering. If isn't, they will alerted by the location, and it will be removed from their shopping cart. | Given I am a customer, when I order something that isn't available, it will not be ordered and I will receive a notification that it is unavailable | Middleware | 42.7 | 91.664 | M | 4.8
15 | As an owner, the owner wants an updated and clean displayment of restaurant information. | Given I am the owner, when I update information regarding the restuarant, then it will reflect on the website itself | Backend | 42.66 | 91.4066 | H | 1.5
16 | Given a customer, the customer should be able to add a order to the order queue of customer orders. | Given I am a customer, when I place an order, that order will automatically be added to the order queue | Backend | 85.3 | 91.3423 | H | 3.5
17 | Given an employee, the employee should be able to view the order queue of all orders made within the restaurant. | Given I am an aployee, when I attempt to view the order queue, then I will be able to see the internal queue for orders and their information | Backend | 85.29 | 91.3102 | H | 4.4
18 | As a owner, the owner should be able to update any product information as well as any menu change. | Given I am the owner, when I update information regarding the menu, then it will reflect on the website's menu | Backend | 85.26 | 91.2139 | H | 2.4
19 | As a customer, I should be able to pick a location upon placing my order out of all three locations. | Given I am a customer, once I finish an order and select a location, then my order will be sent to that location | Frontend | 106.56 | 70.2175 | M | 3.4
20 | As an employee, the order should reach my location to enter the queue of other orders made within the restaurant. | Given I am an employee, when I receive an order, then it should enter queue | Backend | 74.61 | 61.1246 | M | 3.6
21 | Given an employee, the employee should be able to manually set a timer on when the customer’s order will be ready. | Given a customer, the customer should be able to view how long their order will take. | Backend | 213.13 | 38.526 | L | 3.1
22 | As an employee, the employee wants to know which delivery order is being picked up by whom in order to keep customer orders organized. | Given I am an employee, when a customer places an order for pick up, I will know who will be picking it up | Backend | 63.97 | 38.526 | L | 4.6
23 | As a customer, the customer should be able to view the payment screen with all of their orders listed and submit their order. | Given I am a customer, I would like to see a sub-total count with order details will appear before entering checkout. | Frontend | 32.02 | 38.508 | M | 2.2
24 | Given a customer, the customer should be able to identify food based on their preferences in a simple, organized display made on the menu. | Given I am a customer, when I see a menu item tagged with a symbol, then I will know that the specific item has a characteristic that could abide to a dietary or flavor preference | Frontend | 95.9 | 38.4598 | L | 1.3
25 | As a customer, the customer should be able to view their shopping cart. and check what they have ordered so far. | A shopping cart page should load containing any pending orders before a checkout button, with the option to change quantity | Frontend | 53.32 | 22.3098 | H | 2.3
26 | Given a customer, the customer should be able to contact any given Maui Chicken restaurant location. | Given I am a customer who needs assistance, when I select a phone number for a specified location, then I will be able to call the restaurant and speak to a Maui Chicken worker. | Frontend | 159.87 | 22.2722 | M | 1.4
27 | As an employee, the employee can notify a customer by phone recorded on a log if the order isn't picked up within a set time. | A customer will be called according to the phone number they provided in their order details found in the queue or database logs | Backend | 53.29 | 22.2722 | L | 4.5
28 | As a customer, the customer should be given the ability to pay online by credit card form. | Given I am a customer, I should be able to pay for my order online through a simple click of a button. Furthermore, the payment system should be easy and self intuitive. | Backend | 21.37 | 11.4902 | H | 3.8
29 | As an employee, the employee can notify a customer by phone recorded on a log if the order isn't picked up within a set time. | Given I am an employee, when an order is not picked up on time, then I can notify the customer by checking the number tied to that order | Backend | 42.67 | 11.4339 | L | 4.9
30 | As a owner, I would like to log all orders made by customers in the past and log them for three days. Logs past three days will be deleted. | As a owner, I should be able to review all recorded logs in my database for at least 3 days. After 3 days, these logs will get deleted unless specified. | Backend | 32.02 | 4.8316 | M | 4.9.5
31 | As a owner, the owner should be able to send a receipt about a order that has just been placed to the respective customer. | As a owner, I should be able to provide customer with a receipt regarding the order that they just placed on top of being able to review the customer's order. | Backend | 31.97 | 4.809 | H | 3.1.5
32 | As a customer, the customer should be able to receive a downloadable receipt. | As a customer, when I place my online order, I would like a digital copy of my receipt to review my order. | Frontend | 32.02 | 1.4316 | H | 3.9
33 | Given a customer, the customer will see the restaurant's recommendation at the home page. | As a customer, I would like to see what Maui Chicken has to offer and would like details about the restuarant's recomendations | Frontend | 53.29 | 1.4276 | L | 2.1

## 4182022
2022-04-18
# | Software Requirement | Acceptance Criteria | Module | FP Score | Effort Score | Priority |  | Bold = Main tasks
1 | Given a customer, the customer should be able to make an order. | Given I am a customer who has already placed an order, when I select to review my order, then I will be directed to a page that contains information regarding my previous order. | Frontend | 181.15 | 875.2978 | H | 3.2 | Other = subtasks
2 | Given a customer, the customer should be able to review their orders placed earlier. | Given I am a customer who has already placed an order, when I select to review my order, then I will be directed to a page that contains information regarding my previous order | Frontend | 117.21 | 874.8631 | H | 3.3
3 | Given a customer, the customer will use their device's camera to scan the QR code and obtain the menu | Given I am a customer, when I scan the QR code with my camera, then I will be redirected to the restaurant's website | Frontend | 63.97 | 601.3482 | H | 2.6 | Lead
4 | Given a customer, the customer should be able to know how to cancel their order in a simple manner. | Given I am a customer who wants to cancel an order, when I look on the webpage, then I should be able to view a cancel button and be notified of the process | Frontend | 85.3 | 488.4074 | H | 4.1 | Larry Delgado
5 | Given an owner, the owner's restaurant will generate a global QR code amongst all locations for the customer. | Given I am the owner, when I generate a global QR code for my website, then whenever anyone scans that QR code they will be taken to the restaurant's website | Backend | 159.87 | 391.591 | H | 2.5 | Annie Tran
6 | Given a customer, the customer should be able to see a menu from any web accessible application | Given a customer, the customer should be able to view all products' name, price, and description sold by Maui Chicken. | Frontend | 138.56 | 391.5063 | H | 1.1 | Luke Sunoaka
7 | Given a customer, the customer should be able to select a quantity and purchase a product(s) by clicking on the appropriate field below the description to add to shopping cart. | Given I am a customer, when I increase the quantity for a product I am ordering, then the quantity I have selected will be the quantity accounted for in my order. | Frontend | 138.5 | 390.9979 | H | 1.2 | Nima Fathali Siah
8 | As a owner, the customer should be able to view any changes made to the website so that any special promotions willl not go unnoticed. | Given I am the owner, when I update the website in any way, then the customer should be able to view the changes I have applied. | Frontend | 127.87 | 307.7025 | H | 1.6
9 | Given an owner, the owner should be able to access back-end only website where all order transactions are made. | Given I am an owner, when I log in to the website, then I will be able to access and view information and transactions unviewable otherwise | Backend | 53.37 | 178.9809 | H | 4.2
10 | Given an employee, the employee should be able to access back-end only website where all order transactions are made. | Given I am an employee, when I log in to the website, then I will be able to access and view information and transactions unviewable otherwise | Backend | 53.37 | 178.9809 | H | 4.3
13 | As an owner, the owner wants to promote their Yelp restaurant page on the website. | Given I am the owner, I woud like for my Yelp page to be promoted so that my customer's can see any other customer reviews made. | Frontend | 0.04 | 178.2776 | L | 1.7
14 | As an employee, the employee should be able to manage the menu inventory on whether the menu is still available. | Given I am an employee, when I change inventory for menu items, it should reflect on the website as available or not available | Backend | 42.71 | 91.7284 | M | 4.7
15 | As a customer, the customer should know if a menu item is available upon ordering. If isn't, they will alerted by the location, and it will be removed from their shopping cart. | Given I am a customer, when I order something that isn't available, it will not be ordered and I will receive a notification that it is unavailable | Middleware | 42.7 | 91.664 | M | 4.8
16 | As an owner, the owner wants an updated and clean displayment of restaurant information. | Given I am the owner, when I update information regarding the restuarant, then it will reflect on the website itself | Backend | 42.66 | 91.4066 | H | 1.5
17 | Given a customer, the customer should be able to add a order to the order queue of customer orders. | Given I am a customer, when I place an order, that order will automatically be added to the order queue | Backend | 85.3 | 91.3423 | H | 3.5
18 | Given an employee, the employee should be able to view the order queue of all orders made within the restaurant. | Given I am an aployee, when I attempt to view the order queue, then I will be able to see the internal queue for orders and their information | Backend | 85.29 | 91.3102 | H | 4.4
19 | As a owner, the owner should be able to update any product information as well as any menu change. | Given I am the owner, when I update information regarding the menu, then it will reflect on the website's menu | Backend | 85.26 | 91.2139 | H | 2.4
20 | As a customer, I should be able to pick a location upon placing my order out of all three locations. | Given I am a customer, once I finish an order and select a location, then my order will be sent to that location | Frontend | 106.56 | 70.2175 | M | 3.4
21 | As an employee, the order should reach my location to enter the queue of other orders made within the restaurant. | Given I am an employee, when I receive an order, then it should enter queue | Backend | 74.61 | 61.1246 | M | 3.6
22 | Given an employee, the employee should be able to manually set a timer on when the customer’s order will be ready. | Given a customer, the customer should be able to view how long their order will take. | Backend | 213.13 | 38.526 | L | 3.1
23 | As an employee, the employee wants to know which delivery order is being picked up by whom in order to keep customer orders organized. | Given I am an employee, when a customer places an order for pick up, I will know who will be picking it up | Backend | 63.97 | 38.526 | L | 4.6
24 | As a customer, the customer should be able to view the receipt screen with all of their items listed and submit their order. | Given I am a customer, I would like to see a sub-total count with order details will appear before entering checkout. | Frontend | 32.02 | 38.508 | M | 2.2
25 | Given a customer, the customer should be able to identify food based on their preferences in a simple, organized display made on the menu. | Given I am a customer, when I see a menu item tagged with a symbol, then I will know that the specific item has a characteristic that could abide to a dietary or flavor preference | Frontend | 95.9 | 38.4598 | L | 1.3
26 | As a customer, the customer should be able to view their shopping cart. and check what they have ordered so far. | A shopping cart page should load containing any pending orders before a checkout button, with the option to change quantity | Frontend | 53.32 | 22.3098 | H | 2.3
27 | Given a customer, the customer should be able to contact any given Maui Chicken restaurant location. | Given I am a customer who needs assistance, when I select a phone number for a specified location, then I will be able to call the restaurant and speak to a Maui Chicken worker. | Frontend | 159.87 | 22.2722 | M | 1.4
28 | As an employee, the employee can notify a customer by phone recorded on a log if the order isn't picked up within a set time. | A customer will be called according to the phone number they provided in their order details found in the queue or database logs | Backend | 53.29 | 22.2722 | L | 4.5
29 | As an employee, the employee can notify a customer by phone recorded on a log if the order isn't picked up within a set time. | Given I am an employee, when an order is not picked up on time, then I can notify the customer by checking the number tied to that order | Backend | 42.67 | 11.4339 | L | 4.9
30 | As a owner, I would like to log all orders made by customers in the past and log them for three days. Logs past three days will be deleted. | As a owner, I should be able to review all recorded logs in my database for at least 3 days. After 3 days, these logs will get deleted unless specified. | Backend | 32.02 | 4.8316 | M | 4.9.5
31 | As a owner, the owner should be able to send a receipt about a order that has just been placed to the respective customer. | As a owner, I should be able to provide customer with a receipt regarding the order that they just placed on top of being able to review the customer's order. | Backend | 31.97 | 4.809 | H | 3.1.5
32 | As a customer, the customer should be able to receive a downloadable receipt. | As a customer, when I place my online order, I would like a digital copy of my receipt to review my order. | Frontend | 32.02 | 1.4316 | H | 3.9
33 | Given a customer, the customer will see the restaurant's recommendation at the home page. | As a customer, I would like to see what Maui Chicken has to offer and would like details about the restuarant's recomendations | Frontend | 53.29 | 1.4276 | L | 2.1