## 3822
Risk Matrix
Catastrophic
Critical |  |  | Bug with shopping cart; item will be duplicated, but the quantity hasn't been updated
Negligible | Payment API hasn't been approved | No direct acess to website domain yet

## 32122
Risk Matrix
Catastrophic | Not every button registers | Duplicate html loading in backpage
Critical |  |  | Bug with shopping cart; item will be duplicated, but the quantity hasn't been updated
Negligible | Payment API hasn't been approved | No direct acess to website domain yet

## 4422
Risk Matrix
Catastrophic |  | Mobile Website is not user friendly
Critical |  |  | Order with large individual items may need more data compression
Negligible | Payment API hasn't been approved

## Final
Risk Matrix
Catastrophic
Critical |  |  | Order with large individual items may need more data compression
Negligible | Payment API hasn't been approved | No direct acess to website domain yet